## Defect Tracker
Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks | Milestone
Functional | Fixed image upload validation and preprocessing for low‑quality scans | 2025-09-24 | Closed | Upload module stable | Milestone 1
Model Training | Enabled gradient checkpointing to fix GPU memory overflow | 2025-09-28 | Closed | Model training stable | Milestone 1
Algorithmic | Tuned enhancement model to reduce noise amplification | 2025-10-02 | Closed | Sharper enhanced outputs | Milestone 1
UI/Integration | Fixed API route mismatch affecting report display | 2025-10-07 | Closed | Integrated successfully | Milestone 2
Clinical Summary | Corrected missing symptoms due to tokenizer misalignment | 2025-10-10 | Closed | Summary improved | Milestone 2
ICD‑10 Classification | Added multi‑label support + confidence thresholding | 2025-10-14 | Closed | Codes more reliable | Milestone 2
UI/Validation | Added patient data validation + improved errors | 2025-10-22 | Closed | Better UX | Milestone 3
Backend/API | Optimized inference pipeline reducing latency 40% | 2025-10-26 | Closed | Performance improved | Milestone 3
Integration | Fixed CORS + unified inference response structure | 2025-11-01 | Closed | Integration stable | Milestone 3
Deployment | Resolved dependency conflicts in hosting environment | 2025-11-05 | Closed | Deployment stable | Milestone 4
Functional | Corrected ICD‑10 mapping duplication | 2025-11-12 | Closed | Verified | Milestone 4
UI | Adjusted layout alignment + mobile responsiveness | 2025-11-17 | Closed | Presentation-ready | Milestone 4